## ISO 26000 Implementation matrix
ISO 26000 FREE TOOL - IMPLEMENTATION MATRIX
SOURCE: www.iso26000bestpractices.com - NEN handbook 'The implementation of SR, Best practices and tools for ISO 26000
[5 empty] | ready | [10 empty] | #
| Steps | Deliverables | year | Q1-4 | Y/N | Mgt | HRM | Sales | Purch | Comm | Fin | Prod | Log | QHSE | Puller person | days | Explanation
1 | Communication/stakeholder plan, sphere of influence and reporting | [8 empty] | X |  |  |  |  | Comm. Mgr.
1.1 | Identification of stakeholders | Stakeholder map | 2013 | Q1 | Y | X | X | X | X | X | X | X | X | X | Head of Departm. | 3 | Define also stakeholder categories
1.2 | Determine forms of communication (per stakeholder category) | Comm./Stakeholder Plan (matrix) | 2013 | Q3-4 | N | X | X | X | X | X |  |  |  |  | Comm. Mgr. | 5 | Integrate stakeholder plan into comm. plan
1.3 | Analysing stakeholder interests | Stakeholder interests | 2013 | Q2-4 | N | X | X | X | X | X | X | X | X | X | Head of Departm. | 20 | All relevant stakeholders
1.4 | Analysing sphere of influence (SOI) - inside & oustide value chain | Spehere of influence 1st analysis | 2013 | Q4 | N | X |  | X | X | X | X |  |  |  | Chairman SR group | 5 | After stakeholder consultations
1.5 | Determine communication of SR icons | SR Icon comm. (in corp.comm.plan) | 2013 | Q3-4 | N | X | X | X | X | X |  |  |  |  | Comm. Mgr. | 2 | Is part of stakeholder/communication plan
1.6 | Determine way(s) of SR reporting | Repporting structure (f.e. GRI?) | 2013 | Q4 | N | X |  |  |  | X | X |  |  |  | Finance Mgr. | 3 | Combine with finan. reporting; investigate GRI
= Example for step 1
2 | SR issues and actions: determine Relevance, Significance and Priority | [10 empty] | X |  | X
2.1 | Issue matrix: determine relev-signif. (own analysis) of SR issues | Issue matrix (own analysis) | [14 empty] | will be input for stakeholder consultation
2.2 | Update issue matrix after stakeholder consultations | Issue matrix (incl. stakeholder-consult.) | [14 empty] | make questions per stakeholder group
2.3 | Determine SR level of ambition and priority for action (for relevant issues) | SR priorities | [14 empty] | priority of attention versus priority of action
2.4 | Determine SR front and back garden; choose SR Icons | SR front and back garden; SR Icons | [14 empty] | determine competitive advantage with SR
2.5 | Define and update action plans | SR action plans | [14 empty] | connect to daily operations
3 | SR in vision, policy and strategy |  |  |  |  | X
3.1 | Review vision, mission and strategy on SR according to ISO 26000 | Vision, mission, strategy reviewed | [14 empty] | Integrate SR into existing vision, mission
3.2 | Formulate/update SR policy (use results of step 2) + define concrete SR goals | One coherent SR policy + SR goals | [14 empty] | F.e. 3 pages in general + 1 page per departm.
3.3 | Adopt 7 SR Principles into governance (decision making at all levels) | Update govern. doc. + code of conduct | [14 empty] | discuss with board and shareholders
3.4 | Investigate applying Total Cost of Ownership (TCO) at design, purchasing, prod. etc. | TCO investigation & application plan | [14 empty] | consult branch organ. and value chain
3.5 | Investigate applying Life Cycle Analysis (LCA) at design, purchasing, production etc. | LCA investigation & application plan | [14 empty] | use also UNEP environmental and social LCA
4 | Increase SR awareness, develop SR competences (and integrate into HRM) | [5 empty] | X
4.1 | Increase SR awareness for employees, workers, mgt. (information, training etc.) | SR awareness plan (employees, mgt.) | [14 empty] | from unconscious to conscious skilled
4.2 | Develop SR competences with employees and mgt. (knowledge, behaviour, skills) | SR training plan (employees, mgt.) | [14 empty] | combine knowledge, behaviour & skills for SR
4.3 | Integrate SR compet. in roles and functions, develop SR rewarding mechanism | Roles, functions, rewarding incl. SR | [14 empty] | include role of SR ambassador
5 | Integrate SR into existing systems and processes | [12 empty] | X
5.1 | Integrate SR (and ISO 26000) into mgt systems (f.e. ISO 9001, ISO 14001) | Updated mgt. System | [14 empty] | use existing mgt system as basis
5.2 | Integrate SR into project mgt. and tools | SR in project mgt. and tools; | [14 empty] | 7 core subjects in project mgt where possible
5.3 | Integrate SR into work meetings, daily procedures | SR in work meetings and procedures | [14 empty] | stimulate SR dialogue at all levels
5.4 | Integrate SR into products and services (incl. design, manufactoring, maint. etc.) | Products & services plan incl. SR | [14 empty] | search for competitive advantage; collaborate
5.5 | Monitor and measure SR performances: determine performance indicators for SR | KPIs for SR + measurement plan | [14 empty] | have a look at GRI indicators
5.6 | Define sustainable procurement policy and SR supplier code | SR procur. policy and supplier code | [14 empty] | dialogue first, supplier code second
5.7 | Define structured stakeholder communication processes | Stakeholder communication process | [14 empty] | SR commun needs structure and process
6 | Select and apply proper SR initiatives and instruments | [8 empty] | X
6.1 | Analyse existing SR initiatives and instrum. towards ISO 26000; define SR criteria | Current list + new SR criteria | [14 empty] | Define SR criteria and focus on core business
6.2 | Select proper SR initiatives and instruments; define clear SR sponsor policy | Updated list + SR sponsor policy | [14 empty] | Define transparent sponsor policy for SR
7 | Verify SR performances | [9 empty] | X |  |  | X
7.1 | Verify SR performances by employees, workers and mgt. (internal stakeholders) | Internal verification | [14 empty] | Use the power & ideas of your own people
7.2 | Verify SR performances by customers, suppliers, NGOs etc. (external stakeholders) | External verification | [14 empty] | include SR in customer satisfaction investigation
7.3 | Produce a Self Declaration ISO 26000 with practical examples and evidence | ISO 26000 Self Declaration | [14 empty] | Start with option 1: clear report with evidence